## Sheet1
Code | Task Name | Description | Project Manager (Man-Days) | Business Analyst (Man-Days) | Solution/Integration Architect (Man-Days) | Developer (Man-Days) | Tester (Man-Days)
Planning & Discovery
1.1 | Project Plan Development | Development of project plan with resources
1.2 | Discovery Workshop(s) | Discovery workshops to elicit requirements from the client
Design
2.1 | Develop High-level Architecture | Overall & abstract view of the current & target solution
2.2 | Develop Low-level Architecture | Detailed & specific design of the current & target solution
2.3 | Design Documentation
2.4 | Design Walk-Through Workshop(s)
2.5 | Proof of Concept | If required POC to validate the design
Implementation
3.1 | Integration Environment Readiness | Activities to ensure source & target enviromnents are ready for integration
3.2 | Landing Zone Configuration | Landng zones for Azure environment
3.3 | DevOps Environment Configuration | Establish DevOps projects, configurations & repos for the assignment
3.4 | Specific AIS Component Configuration | Configure LogicApps, Servce Bus, Event Grid, Function Apps, Azure Data Factory & Storage Accounts
3.5 | Development of Components | Development of Azure Functions, Logc Apps
3.6 | Implement Disaster Recovery & High Availability | Implement components required for DR & HA
3.7 | Data Migration | Data migration if required
Testing
4.1 | Unit Testing | Implement unit tests for Azure functions & logic apps
4.2 | Integration Testng
4.3 | Vulnerability Assessment & Penetration Testing | Use Azure Security Center & other tools to perform testing
4.4 | User Acceptance Testng
Deployment
5.1 | Configure CI/CD Pipelines
5.2 | Deployment to Non-Prod Environments
5.3 | Deployment to Prod Environments
5.4 | Post-Deployment Verification
Closure
6.1 | Establish Monitoring & Logging | Implementation & consumption of Azure Monitor
6.2 | Issue Resolution
6.3 | Project Closure Documentation